## CMAQ_FY14-19 (Final)
MPO Regional Priority Projects for CMAQ FY 14-19 |  |  |  | Phase | Total Project Cost |  | Tri-Cities MPO CMAQ Allocations for FY 14-19 SYIP | [18 empty] | Balance to Complete after FY-19 | Comments
No. | Jurisdiction | UPC | Project Description |  |  | Previous Allocations | FY-14 | FY-14 80% | FY-14 20% | FY-15 | FY-15 80% | FY-15 20% | FY-16 | FY-16 80% | FY-16 20% | FY-17 | FY-17 80% | FY-17 20% | FY-18 | FY-18 80% | FY-18 20% | FY-19 | FY-19 80% | FY-19 20% | Total Allocations FY 14-19
1 | Regionwide | T204 | Ridefinders for Tri-Cities | PE | 435000 |  | 16000 | 12800 | 3200 | 35000 |  |  | 35000 |  |  | 35000 |  |  | 35000 |  |  | 35000 |  |  |  |  | Increased Yearly Allocation to 35K in FY-15. Estimate in PCES needs to be increased to $435k to fully balance allocations to estimate.
|  |  |  | Total | 435000 | 244000 | [18 empty] | 191000 | 0
2 | Chesterfield | 90367 | Route 1 NB right turn lane at Woods Edge Road | PE | 135000 | [21 empty] | RW Estimate increased, project needed an additional $35,930 to be fully funded.
|  |  |  | RW | 300000
|  |  |  | CN | 341106 |  | 0 |  |  | 267205
|  |  |  | Total | 776106 | 508901 | [18 empty] | 267205 | 0
3 | Chesterfield | 98994 | Route 144 Harrowgate Road & South Street (turn ln & sdwlk | PE | 354908 | [21 empty] | Project delayed by one year due to FY-14 funding cut. RW Phase will be delayed until FY15 funds are available which would be 7/1/2014, so that is a delay at minimum of 4 months. CN Phase will be delayed until FY16 Funds are available which would be 7/1/2015, so that is a minimum delay of 3 months. Construction would be completed in 1 year then we have 1 year to fully fund after completion, which will give us until FY18.
|  |  |  | RW | 349319 |  | 0 |  |  | 234227
|  |  |  | CN | 804591 | [7 empty] | 445816 |  |  | 84381 |  |  | 274394
|  |  |  | Total | 1508818 | 470000 | [18 empty] | 1038818 | 0
4 | Colonial Heights | 98882 | Route 144 Temple & Conduit Intersection Improvement, extend a right turn LN from W/B Temple Ave. onto N/B Conduit | PE | 65000
|  |  |  | RW | 0
|  |  |  | CN | 385000 |  | 145000 | 116000 | 29000
|  |  |  | Total | 450000 | 305000 | [18 empty] | 145000 | 0
5 | Colonial Heights | 3945 | Route 1/Dupuy Avenue (intersection) | PE | 740000 | [21 empty] | Overfunding shown due to $1,874,676 of Rev Sh Funds and $1,874,676 of City matching funds in the SYIP, which the City has requested the Rev Sh funds be de-allocated (they do not have their matching funds). This de-allocation to be done by CTB.
|  |  |  | RW | 1960000
|  |  |  | CN | 3946296 |  | 464976 | 371980.8 | 92995.2 | 134526
|  |  |  | Total | 6646296 | 9796146 | [18 empty] | 599502 | -3749352
6 | Colonial Heights | 99194 | Branders Bridge Road & Route 1 intersection | PE | 35000 |  |  |  |  | 0 | [5 empty] | 35000 | [10 empty] | City requested MPO to move funds to fully fund UPC 3945 because they did not have their match for the Rev Sh Funds, 3945 was ready to go to advertisement. MPO & City agreed to move funds from this project and delay it to fully fund a higher priority. Schedule in system needs to be updated.
|  |  |  | RW | 0
|  |  |  | CN | 210000 | [13 empty] | 210000
|  |  |  | Total | 245000 | 0 | [18 empty] | 245000 | 0
7 | Colonial Heights | 98883 | Route 144 Temple Avenue Corridor Signal Coordination | PE | 100000 |  |  |  |  | 0 | [5 empty] | 100000 | [10 empty] | City requested MPO to move funds to fully fund UPC 3945 because they did not have their match for the Rev Sh Funds, 3945 was ready to go to advertisement. MPO & City agreed to move funds from this project and delay it to fully fund a higher priority. Schedule in system needs to be updated.
|  |  |  | RW | 0
|  |  |  | CN | 395000 | [13 empty] | 111304 |  |  | 283696
|  |  |  | Total | 495000 | 0 | [18 empty] | 495000 | 0
8 | Colonial Heights | 100501 | Route 1 & Westover Avenue | PE | 125000 | [7 empty] | 0 | 0 | 0 | 0 |  |  | 125000 | [7 empty] | City requested MPO to move funds to fully fund UPC 3945 because they did not have their match for the Rev Sh Funds, 3945 was ready to go to advertisement. MPO & City agreed to move funds from this project and delay it to fully fund a higher priority. Schedule in system needs to be updated.
|  |  |  | RW | 19000 | [16 empty] | 19000
|  |  |  | CN | 655893 | [16 empty] | 62085
|  |  |  | Total | 799893 | 0 | [18 empty] | 144000 | 655893
9 | Hopewell | 12955 | Hopewell - Rte 10 Improve Intersection | PE | 266150
|  |  |  | RW | 142034
|  |  |  | CN | 853072 |  |  | 0 | 0 | 320053 |  |  | 20045
|  |  |  | Total | 1261256 | 921158 | [18 empty] | 340098 | 0
10 | Hopewell | 100500 | Route 36 WBL at Jefferson Park Road | PE | 72600 | [21 empty] | Currently only a PE Project, Schedule will need to be updated to add RW & CN Phases. Estimate in PCES needs to be updated. All phases fully funded
|  |  |  | RW | 50000 | [7 empty] | 50000
|  |  |  | CN | 227400 | [10 empty] | 227400
|  |  |  | Total | 350000 | 72600 | [18 empty] | 277400 | 0
11 | Petersburg | 101039 | South Crater Rd Area Signal Coordination | PE | 132000 |  |  |  |  | 132000
|  |  |  | RW | 0
|  |  |  | CN | 528000 | [10 empty] | 528000
|  |  |  | Total | 660000 | 0 | [18 empty] | 660000 | 0
12 | Petersburg | 101289 | VNDIA Fort Lee Area BRAC Project for Puddledock Rd Intersection @ Industrial Drive | PE | 50000 |  | 50000 | 40000 | 10000 | [17 empty] | This is one of several VNDIA Fort Lee Area BRAC projects in the Tri-Cities Area. This project intersection area was identified as a deficiency in the Fort Lee Study. VNDIA funds will pay for half of project cost and must be matched by any funding source. VNDIA Allocations need to be allocated in FY14 or FY15. Also, VNDIA Allocations are not shown in SYIP, but the project is fully funded with CMAQ Funds. Balance to complete is VNDIA Allocations amount.
|  |  |  | PE-VNDIA | 50000
|  |  |  | RW | 0
|  |  |  | RW-VNDIA | 0
|  |  |  | CN | 211770 |  |  |  |  | 211770
|  |  |  | CN-VNDIA | 210000
|  |  |  | Total | 521770 | 0 | [18 empty] | 261770 | 260000
13 | Petersburg | T13352 | Petersburg - Vehicle Detection - 30 Intersections | PE | 150000 | [7 empty] | 150000 | [13 empty] | NEED TO ADJUST SCHEDULE IN SYSTEM TO BE PE STATE AS 12/1/2015 AND CN DATE AS 12/1/2016
|  |  |  | RW | 0
|  |  |  | CN | 300000 | [10 empty] | 300000
|  |  |  | Total | 450000 | 0 | [18 empty] | 450000 | 0
14 | Petersburg | T13353 | Petersburg - Citywide Signal Retiming | PE | 180000 | [13 empty] | 180000
|  |  |  | RW | 0
|  |  |  | CN | 0
|  |  |  | Total | 180000 | 0 | [18 empty] | 180000 | 0
15 | Petersburg | T13354 | Extend LTL S. Crater Rd. & Morton | PE | 100000 | [13 empty] | 100000 | [7 empty] | NEED TO ADJUST SCHEDULE IN SYSTEM TO BE PE START AS 12/1/2017 AND CN DATE AS 12/1/2018
RW
|  |  |  | CN | 450000 | [16 empty] | 450000
|  |  |  | Total | 550000 | 0 | [18 empty] | 550000 | 0
16 | Petersburg | T13355 | S. Crater Road at Medical Park Boulevard | PE | 50000 | [13 empty] | 50000
RW
|  |  |  | CN | 285000 | [16 empty] | 285000
|  |  |  | Total | 335000 | 0 | [18 empty] | 335000 | 0
17 | Petersburg | T13356 | Petersburg Signal Upgrade | PE | 200000 | [16 empty] | 200000 |  |  |  |  | NEED TO ADJUST SCHEDULE IN SYSTEM TO BE PE START AS 12/1/2018 AND CN DATE AS 12/1/2019
RW
|  |  |  | CN | 1400000
|  |  |  | Total | 1600000 | 0 | [18 empty] | 200000 | 1400000
18 | Prince George | 97635 | Rte 156 @ Rt 616 Intersection Improvements | PE | 350000 | [21 empty] | Total Estimate was just decreased from $1,798,854 to $1,545,042 on 3/16/13, resulting in project now being overfunded. AD 3/12/13
|  |  |  | RW | 239826
|  |  |  | CN | 955216 |  | 313005 | 250404 | 62601
|  |  |  | Total | 1545042 | 1479297 | [18 empty] | 313005 | -247260
19 | Prince George | 82849 | CONSTRUCT LT LANE NB ON RTE 630 ONTO RTE 460 FOR WB TRAFFIC | PE | 25000 | [10 empty] | 25000 | [10 empty] | SYIP CURRENTLY SHOWS PREV FUNDS OF $339,055 - THESE FUNDS NEED TO BE MOVED TO BALANCE ENTRY ACCOUNT OR ANOTHER PROJECT
|  |  |  | RW | 0
|  |  |  | CN | 249083 | [13 empty] | 249083
|  |  |  | Total | 274083 | 339055 | [18 empty] | 274083 | -339055
20 | Prince George | 100499 | Rte 460 - Add WB LTL at Rte 657 | PE | 280000
|  |  |  | RW | 220000
|  |  |  | CN | 755017 | [7 empty] | 633920
|  |  |  | Total | 1255017 | 621097 | [18 empty] | 633920 | 0
[7 empty] | FY-14 |  |  | FY-15 |  |  | FY-16 |  |  | FY-17 |  |  | FY-18 |  |  | FY-19 |  |  | Balance to Complete | 1469578
Legend |  |  |  | New CMAQ Budget |  |  | 988981 |  |  | 1334781 |  |  | 1334781 |  |  | 1334781 |  |  | 1334781 |  |  | 1334781
| New VNDIA Fort Lee BRAC Area Project |  |  | Old CMAQ Budget |  |  | 1668871 |  |  | 1711664 |  |  | 1739187 |  |  | 1801394 |  |  | 1869767 |  |  | NA
| New Project |  |  | Map-21 Reduction |  |  | -679890 |  |  | -376883 |  |  | -404406 |  |  | -466613 |  |  | -534986 |  |  | NA
| Revised FY14-19 Funding (new or adjusted) |  |  | Total Allocations |  |  | 988981 |  |  | 1334781 |  |  | 1334781 |  |  | 1334781 |  |  | 1334781 |  |  | 1334781
| Removed from that FY |  |  | Balance |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
NEW PROJECTS THAT WERE NOT SELECTED:
20 | City of Petersburg |  | S. Crater Rd. at Sycamore St. | PE | 100000
|  |  |  | RW | 150000
|  |  |  | CN | 750000
|  |  |  | Total | 1000000
21 | City of Petersburg |  | S. Crater Rd. LTL at Wal-Mart entrance | PE | 20000
RW
|  |  |  | CN | 150000
|  |  |  | Total | 170000
22 | City of Petersburg |  | S. Crater Rd. at Flank Rd. | PE | 90000
|  |  |  | RW | 100000
|  |  |  | CN | 400000
|  |  |  | Total | 590000
23 | City of Petersburg |  | S. Crater Rd. at Graham Rd. RTL | PE | 95000
|  |  |  | RW | 100000
|  |  |  | CN | 500000
|  |  |  | Total | 695000
24 | City of Petersburg |  | Johnson Rd. at South Boulevard | PE | 100000
|  |  |  | RW | 150000
|  |  |  | CN | 500000
|  |  |  | Total | 750000
25 | City of Petersburg |  | Petersburg crash truck | PE
RW
|  |  |  | CN | 150000
Total
26 | City of Petersburg |  | 6 PAT buses | PE
RW
|  |  |  | CN | 2400000
|  |  |  | Total | 2400000
27 | City of Petersburg |  | N. Normandy Dr. at Wagner Rd. | PE | 85000 | [21 empty] | Application total lists 835,000, but 85,000 for PE and 450,000 for CN.
RW
|  |  |  | CN | 450000
|  |  |  | Total | 535000
28 | City of Petersburg |  | S. Crater Road at Wagner RTL | PE | 35000
|  |  |  | RW | 75000
|  |  |  | CN | 275000
|  |  |  | Total | 385000
29 | Prince George |  | Rt. 106 & Rt. 616 | PE | 165000
|  |  |  | RW | 275000
|  |  |  | CN | 245900
|  |  |  | Total | 685900
30 | City of Petersburg |  | Petersburg Park & Ride Lot | PE | 200000
RW
|  |  |  | CN | 1000000
|  |  |  | Total | 1200000
Note on H7: Sherry.Eagle: Project had FY14 funds last year. This is a funding delay so it's in grey
Note on H10: Sherry.Eagle: Project had FY14 funds last year. This is a funding delay so it's in grey
Note on K21: Sherry.Eagle: Project had FY15 funds last year. This is a funding delay so it's in grey
Note on K25: Sherry.Eagle: Project had FY15 funds last year. This is a funding delay so it's in grey
Note on N29: Sherry.Eagle: Project had FY16 funds last year. This is a funding delay so it's in grey
Note on O29: Sherry.Eagle: Project had FY15 funds last year. This is a funding delay so it's in grey
Note on P29: Sherry.Eagle: Project had FY15 funds last year. This is a funding delay so it's in grey
Note on Q29: Sherry.Eagle: Project had FY17 funds last year. This is a funding delay so it's in grey
Note on N49: Sherry.Eagle: Last year Plan indicated FY16 $, however we moved it all to FY15
Note on Q49: Sherry.Eagle: Last year Plan indicated FY17 $, however we moved it all to FY15
Note on AA51: Sherry.Eagle: Balance to complete will be with VNDIA Allocations
Note on G79: Sherry.Eagle: SYIP SHOWS PREV ALLOC - THIS NEEDS TO BE MOVED OFF AND TO BE ACCOUNT
Note on AA85: Sherry.Eagle: This subtracts out the VNDIA Funds above of $260k

## CMAQ_FY14-19_Formulas
MPO Regional Priority Projects for CMAQ FY 14-19 |  |  |  | Phase | Total Project Cost | Tri-Cities MPO CMAQ Allocations for FY 14-19 SYIP | [6 empty] | Balance to Complete after FY-19 | Comments
No. | Jurisdiction | UPC | Project Description |  |  | FY-14 | FY-15 | FY-16 | FY-17 | FY-18 | FY-19 | Total Allocations FY 14-19
1 | Regionwide | T204 | Ridefinders for Tri-Cities | PE | 403000 | 16000 | 35000 | 35000 | 35000 | 35000 | 35000 | 191000 | 0 | Increased Yearly Allocation to 35K in FY-15
2 | Chesterfield | 90367 | Route 1 NB right turn lane at Woods Edge Road | PE | 135000 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | Need $35,930 for add'l RW in FY-15
|  |  |  | RW | 335930 | 0 | 35930 | 0 | 0 | 0 | 0 | 35930 | 0
|  |  |  | CN | 305176 | 0 | 231275 | 0 | 0 | 0 | 0 | 231275 | 0
3 | Chesterfield | 98994 | Route 144 Harrowgate Road & South Street (turn ln & sdwlk | PE | 354908 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project delayed by one year due to FY-14 funding cut.
|  |  |  | RW | 349319 | 0 | 234227 | 0 |  | 0 | 0 | 234227 | 0
|  |  |  | CN | 804591 | 0 | 0 | 385698 | 275623 | 143270 | 0 | 804591 | 0
4 | Colonial Heights | 98882 | Route 144 Temple & Conduit Intersection Improvement, extend a right turn LN from W/B Temple Ave. onto N/B Conduit | PE | 65000 | Tri-Cities MPO CMAQ Allocations for FY 14-19 SYIP FY-14: 0 | 0 | 0
|  |  |  | RW | 0 | Tri-Cities MPO CMAQ Allocations for FY 14-19 SYIP FY-14: 0 | 0 | 0
|  |  |  | CN | 385000 | Tri-Cities MPO CMAQ Allocations for FY 14-19 SYIP FY-14: 145000 | 145000 | 0
5 | Colonial Heights | 3945 | Route 1/Dupuy Avenue (intersection) | PE | 740000 | Tri-Cities MPO CMAQ Allocations for FY 14-19 SYIP FY-14: 0 | 0 | 0
|  |  |  | RW | 1960000 | Tri-Cities MPO CMAQ Allocations for FY 14-19 SYIP FY-14: 0 | 0 | 0
|  |  |  | CN | 3946296 | Tri-Cities MPO CMAQ Allocations for FY 14-19 SYIP FY-14: 384088; Tri-Cities MPO CMAQ Allocations for FY 14-19 SYIP FY-15: 215414 | 599502 | 0
6 | Colonial Heights | 99194 | Branders Bridge Road & Route 1 intersection | PE | 35000 | 0 |  |  | 35000 | 0 | 0 | 35000 | 0
|  |  |  | RW | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | CN | 210000 | 0 |  |  | 0 | 210000 | 0 | 210000 | 0
7 | Colonial Heights | 98883 | Route 144 Temple Avenue Corridor Signal Coordination | PE | 100000 | Tri-Cities MPO CMAQ Allocations for FY 14-19 SYIP FY-14: 0; Tri-Cities MPO CMAQ Allocations for FY 14-19 SYIP FY-18: 100000; Tri-Cities MPO CMAQ Allocations for FY 14-19 SYIP FY-19: 0 | 100000 | 0
|  |  |  | RW | 0 | Tri-Cities MPO CMAQ Allocations for FY 14-19 SYIP FY-14: 0; Tri-Cities MPO CMAQ Allocations for FY 14-19 SYIP FY-18: 0; Tri-Cities MPO CMAQ Allocations for FY 14-19 SYIP FY-19: 0 | 0 | 0
|  |  |  | CN | 395000 | Tri-Cities MPO CMAQ Allocations for FY 14-19 SYIP FY-14: 0; Tri-Cities MPO CMAQ Allocations for FY 14-19 SYIP FY-18: 0; Tri-Cities MPO CMAQ Allocations for FY 14-19 SYIP FY-19: 395000 | 395000 | 0
8 | Colonial Heights | 100501 | Route 1 & Westover Avenue | PE | 125000 | Tri-Cities MPO CMAQ Allocations for FY 14-19 SYIP FY-14: 0; Tri-Cities MPO CMAQ Allocations for FY 14-19 SYIP FY-19: 125000 | 125000 | 0
|  |  |  | RW | 19000 | Tri-Cities MPO CMAQ Allocations for FY 14-19 SYIP FY-14: 0; Tri-Cities MPO CMAQ Allocations for FY 14-19 SYIP FY-18: 0; Tri-Cities MPO CMAQ Allocations for FY 14-19 SYIP FY-19: 19000 | 19000 | 0
|  |  |  | CN | 655893 | Tri-Cities MPO CMAQ Allocations for FY 14-19 SYIP FY-14: 0; Tri-Cities MPO CMAQ Allocations for FY 14-19 SYIP FY-18: 0; Tri-Cities MPO CMAQ Allocations for FY 14-19 SYIP FY-19: 0 | 0 | 655893
8 | Hopewell | 12955 | Hopewell - Rte 10 Improve Intersection | PE | 266150 | Tri-Cities MPO CMAQ Allocations for FY 14-19 SYIP FY-14: 0; Tri-Cities MPO CMAQ Allocations for FY 14-19 SYIP FY-15: 0; Tri-Cities MPO CMAQ Allocations for FY 14-19 SYIP FY-16: 0 | 0 | 0
|  |  |  | RW | 142034 | Tri-Cities MPO CMAQ Allocations for FY 14-19 SYIP FY-14: 0; Tri-Cities MPO CMAQ Allocations for FY 14-19 SYIP FY-15: 0; Tri-Cities MPO CMAQ Allocations for FY 14-19 SYIP FY-16: 0 | 0 | 0
|  |  |  | CN | 853072 | Tri-Cities MPO CMAQ Allocations for FY 14-19 SYIP FY-14: 80888; Tri-Cities MPO CMAQ Allocations for FY 14-19 SYIP FY-15: 251165; Tri-Cities MPO CMAQ Allocations for FY 14-19 SYIP FY-16: 0 | 332053 | 0
9 | Hopewell | 100500 | Route 36 WBL at Jefferson Park Road | PE | 72600 | 0 | 0 | 0 | 0 |  |  | 0 | 0
|  |  |  | RW | 50000 | 0 | 0 | 50000 | 0 |  |  | 50000 | 0
|  |  |  | CN | 227400 | Tri-Cities MPO CMAQ Allocations for FY 14-19 SYIP FY-16: 0; Tri-Cities MPO CMAQ Allocations for FY 14-19 SYIP FY-17: 227400 | 227400 | 0
10 | Petersburg | 101039 | South Crater Rd Area Signal Coordination | PE | 132000 | 0 | 120000 | 12000 | 0 |  |  | 132000 | 0
|  |  |  | RW | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
|  |  |  | CN | 528000 | Tri-Cities MPO CMAQ Allocations for FY 14-19 SYIP FY-16: 258000; Tri-Cities MPO CMAQ Allocations for FY 14-19 SYIP FY-17: 270000 | 528000 | 0
11 | Petersburg | 101289 | VNDIA Fort Lee Area BRAC Project for Puddledock Rd Intersection @ Industrial Drive | PE | 50000 | 50000 | 0 | 0 | 0 |  |  | 50000 | 0 | This is one of several VNDIA Fort Lee Area BRAC projects in the Tri-Cities Area. This project intersection area was identified as a deficiency in the Fort Lee Study. VNDIA funds will pay for half of project cost and must be matched by a MPO funding source such as CMAQ or RSTP.
|  |  |  | PE-VNDIA | 50000 | [6 empty] | 0
|  |  |  | RW | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
|  |  |  | RW-VNDIA | 0 | [6 empty] | 0
|  |  |  | CN | 211770 | Tri-Cities MPO CMAQ Allocations for FY 14-19 SYIP FY-15: 211770; Tri-Cities MPO CMAQ Allocations for FY 14-19 SYIP FY-16: 0; Tri-Cities MPO CMAQ Allocations for FY 14-19 SYIP FY-17: 0 | 211770 | 0
|  |  |  | CN-VNDIA | 210000 | Tri-Cities MPO CMAQ Allocations for FY 14-19 SYIP FY-16: 0; Tri-Cities MPO CMAQ Allocations for FY 14-19 SYIP FY-17: 0 | 0 | 0
12 | Petersburg | T13352 | Petersburg - Vehicle Detection - 30 Intersections | PE | 150000 | Tri-Cities MPO CMAQ Allocations for FY 14-19 SYIP FY-16: 150000; Tri-Cities MPO CMAQ Allocations for FY 14-19 SYIP FY-17: 0 | 150000 | 0
|  |  |  | RW | 0 | Tri-Cities MPO CMAQ Allocations for FY 14-19 SYIP FY-17: 0 | 0 | 0
|  |  |  | CN | 300000 | Tri-Cities MPO CMAQ Allocations for FY 14-19 SYIP FY-17: 165000; Tri-Cities MPO CMAQ Allocations for FY 14-19 SYIP FY-18: 135000 | 300000 | 0
13 | Petersburg | T13353 | Petersburg - Citywide Signal Retiming | PE | 180000 | Tri-Cities MPO CMAQ Allocations for FY 14-19 SYIP FY-16: 0; Tri-Cities MPO CMAQ Allocations for FY 14-19 SYIP FY-18: 180000 | 180000 | 0
|  |  |  | RW | 0 | Tri-Cities MPO CMAQ Allocations for FY 14-19 SYIP FY-17: 0 | 0 | 0
|  |  |  | CN | 0 | Tri-Cities MPO CMAQ Allocations for FY 14-19 SYIP FY-17: 0 | 0 | 0
14 | Petersburg | T13354 | Extend LTL S. Crater Rd. & Morton | PE | 100000 | Tri-Cities MPO CMAQ Allocations for FY 14-19 SYIP FY-17: 0; Tri-Cities MPO CMAQ Allocations for FY 14-19 SYIP FY-18: 100000 | 100000 | 0
|  |  |  | RW |  | Tri-Cities MPO CMAQ Allocations for FY 14-19 SYIP FY-17: 0 | 0 | 0
|  |  |  | CN | 450000 | Tri-Cities MPO CMAQ Allocations for FY 14-19 SYIP FY-17: 0; Tri-Cities MPO CMAQ Allocations for FY 14-19 SYIP FY-18: 132428; Tri-Cities MPO CMAQ Allocations for FY 14-19 SYIP FY-19: 317572 | 450000 | 0
15 | Petersburg | T13355 | S. Crater Road at Medical Park Boulevard | PE | 50000 | Tri-Cities MPO CMAQ Allocations for FY 14-19 SYIP FY-17: 0; Tri-Cities MPO CMAQ Allocations for FY 14-19 SYIP FY-18: 50000 | 50000 | 0
|  |  |  | RW |  | Tri-Cities MPO CMAQ Allocations for FY 14-19 SYIP FY-17: 0 | 0 | 0
|  |  |  | CN | 285000 | Tri-Cities MPO CMAQ Allocations for FY 14-19 SYIP FY-17: 0; Tri-Cities MPO CMAQ Allocations for FY 14-19 SYIP FY-19: 285000 | 285000 | 0
16 | Petersburg | T13356 | Petersburg Signal Upgrade | PE | 200000 | Tri-Cities MPO CMAQ Allocations for FY 14-19 SYIP FY-17: 0; Tri-Cities MPO CMAQ Allocations for FY 14-19 SYIP FY-18: 0; Tri-Cities MPO CMAQ Allocations for FY 14-19 SYIP FY-19: 158209 | 158209 | 41791
|  |  |  | RW |  | Tri-Cities MPO CMAQ Allocations for FY 14-19 SYIP FY-17: 0; Tri-Cities MPO CMAQ Allocations for FY 14-19 SYIP FY-18: 0; Tri-Cities MPO CMAQ Allocations for FY 14-19 SYIP FY-19: 0 | 0 | 0
|  |  |  | CN | 1400000 | Tri-Cities MPO CMAQ Allocations for FY 14-19 SYIP FY-17: 0; Tri-Cities MPO CMAQ Allocations for FY 14-19 SYIP FY-18: 0; Tri-Cities MPO CMAQ Allocations for FY 14-19 SYIP FY-19: 0 | 0 | 1400000
17 | Prince George | 97635 | Route 36 WBL at Jefferson Park Road | PE | 350000 | [6 empty] | 0 | 0
|  |  |  | RW | 239826 | [6 empty] | 0 | 0
|  |  |  | CN | 955216 | Tri-Cities MPO CMAQ Allocations for FY 14-19 SYIP FY-14: 313005 | 313005 | 0
18 | Prince George | 82849 | CONSTRUCT LT LANE NB ON RTE 630 ONTO RTE 460 FOR WB TRAFFIC | PE | 25000 | Tri-Cities MPO CMAQ Allocations for FY 14-19 SYIP FY-17: 25000; Tri-Cities MPO CMAQ Allocations for FY 14-19 SYIP FY-18: 0 | 25000 | 0
|  |  |  | RW | 0 | Tri-Cities MPO CMAQ Allocations for FY 14-19 SYIP FY-17: 0; Tri-Cities MPO CMAQ Allocations for FY 14-19 SYIP FY-18: 0 | 0 | 0
|  |  |  | CN | 249083 | Tri-Cities MPO CMAQ Allocations for FY 14-19 SYIP FY-17: 0; Tri-Cities MPO CMAQ Allocations for FY 14-19 SYIP FY-18: 249083 | 249083 | 0
19 | Prince George | 100499 | Rte 460 - Add WB LTL at Rte 657 | PE | 280000 | [6 empty] | 0 | 0
|  |  |  | RW | 220000 | [6 empty] | 0 | 0
|  |  |  | CN | 755017 | Tri-Cities MPO CMAQ Allocations for FY 14-19 SYIP FY-16: 444083; Tri-Cities MPO CMAQ Allocations for FY 14-19 SYIP FY-17: 301758 | 745841 | 0
[6 empty] | FY-14 | FY-15 | FY-16 | FY-17 | FY-18 | FY-19 | Balance to Complete | 2097684
Legend |  |  |  | New CMAQ Budget |  | 988981 | 1334781 | 1334781 | 1334781 | 1334781 | 1334781
| New VNDIA Fort Lee BRAC Area Project |  |  | Old CMAQ Budget |  | 1668871 | 1711664 | 1739187 | 1801394 | 1869767 | NA
| New Project |  |  | Map-21 Reduction |  | -679890 | -376883 | -404406 | -466613 | -534986 | NA
| New FY 14-19 Funding |  |  | Total Allocations |  | 988981 | 1334781 | 1334781 | 1334781 | 1334781 | 1334781
| FY 14-19 Funding Moved Up to Earlier Years |  |  | Balance |  | 0 | 0 | 0 | 0 | 0 | 0
FY 14-19 Funding Delayed to Later Years